## Road-Map
Item. No. | Script/Activity Name | Parameter List | Script File Name | Owner Name | Automation Type | Start Date | Expected end date | Actual Completion Date | Status | Comments
1 | Create Backup Vault | Parameters List | Create-AzureRMBackupVault.ps1 | SavindraSingh | Through Cloud | 2016-05-16 | 2016-06-03 | 2016-06-02 | Script-Ready
2 | Configure Backup Job/Policy | Parameters List | Configure-BackupPolicy.ps1 | SavindraSingh | On-Premise | 2016-05-16 | 2016-06-03 | 2016-06-02 | Script-Ready | ON PREM SCRIPT - ON HOLD
3 | Create Azure RM Storage Account (JSON) | Parameters List | Create-AzureRMStorageAccountFromTemplate.ps1 | SavindraSingh | Through Cloud | 2016-05-26 | 2016-06-03 | 2016-06-03 | Script-Ready
4 | Create Virtual Network (JSON) | Parameters List | Create-AzureRMVNetFromTemplate.ps1 | SavindraSingh | Through Cloud | 2016-05-16 | 2016-06-03 | 2016-06-02 | Script-Ready
5 | Create ARM VM From Gallery Image (JSON) | Parameters List | Create-ARMVMFromGalleryImage.ps1 | Bhaskar | Through Cloud | 2016-05-16 | 2016-06-03 | 2016-07-04 | Script-Ready
6 | Create ARM VM From custom Image (JSON) | Parameters List | Create-ARMVMFromCustomImage.ps1 | Bhaskar | Through Cloud | 2016-05-16 | 2016-06-03 | 2016-07-05 | Script-Ready
7 | Get list of Resource Groups | Parameters List | Get-ListOfResourceGroupNames.ps1 | SavindraSingh | Through Cloud | 2016-05-26 | 2016-06-03 | 2016-06-03 | Completed | Script for GUI
8 | Get list of Virtual Machines | Parameters List | Get-ListOfVirtualMachines.ps1 | SavindraSingh | Through Cloud | 2016-05-26 | 2016-06-03 | 2016-06-03 | Completed | Script for GUI
9 | Get list of Virtual Networks | Parameters List | Get-ListOfVNets.ps1 | SavindraSingh | Through Cloud | 2016-05-26 | 2016-06-03 | 2016-06-03 | Completed | Script for GUI
10 | Get list of Virtual Network Subnets | Parameters List | Get-ListOfVNetSubnets.ps1 | SavindraSingh | Through Cloud | 2016-05-26 | 2016-06-03 | 2016-06-07 | Completed | Script for GUI
11 | Get list of VM Sizes (from Location) | Parameters List | Get-ListOfVMSizes.ps1 | SavindraSingh | Through Cloud | 2016-05-26 | 2016-06-10 | 2016-06-07 | Completed | Script for GUI
12 | Backup Azure IIS VM | Parameters List | Backup-AzureIISVM.ps1 | SavindraSingh | Through Cloud | 2016-06-10 | 2016-06-15 | 2016-06-27 | Script-Ready
13 | Setup Azure Backup Server | Parameters List | NA | Bhaskar | On-Premise | 2016-07-11 | 2016-07-14 | NA | NA
14 | Configure Azure Backup Server | Parameters List | NA | Bhaskar | On-Premise | 2016-07-11 | 2016-07-15 | NA | NA
15 | Setup Azure Backup Agent (Files/Folders) | Parameters List | NA | Bhaskar | On-Premise | 2016-07-11 | 2016-07-13 | NA | NA
16 | Create NSG and Apply NSG Rules | Parameters List | Create-NSGAndConfigureRules.ps1 | Bhaskar | Through Cloud | 2016-07-21 | 2016-07-21 | 2016-07-22 | Script-Ready
17 | Map NSG to subnet | Parameters List | Create-NSGAndConfigureRules.ps1 | Bhaskar | Through Cloud | 2016-07-20 | 2016-07-20 | 2016-07-20 | Script-Ready
18 | (OR) Map NSG to VM | Parameters List | Attach-NSGToVM.ps1 | Bhaskar | Through Cloud | 2016-07-20 | 2016-07-20 | 2016-07-20 | Script-Ready
19 | Add local area network (Hybrid) Create gateway for local area network (Hybrid) | Parameters List | Configure-HybridNetwork.ps1 | Bhaskar | Through Cloud | 2016-07-25 | 2016-07-28 | 2016-07-28 | Script-Ready
20 | Add the VM to existing domain as member server | Parameters List | Add-AzureVMToDomain.ps1 | Bhaskar | Through Cloud | 2016-07-19 | 2016-07-19 | 2016-07-19 | Script-Ready
21 | Get List of VM Image Offers | Parameters List | Get-ListOfImageOffers.ps1 | SavindraSingh | Through Cloud | 2016-08-04 | 2016-08-04 | 2016-08-04 | Completed | Script for GUI
22 | Get List of VM Image Publishers | Parameters List | Get-ListOfImagePublishers.ps1 | SavindraSingh | Through Cloud | 2016-08-04 | 2016-08-04 | 2016-08-04 | Completed | Script for GUI
23 | Get List of VM Image SKUs | Parameters List | Get-ListOfImageSKUs.ps1 | SavindraSingh | Through Cloud | 2016-08-04 | 2016-08-04 | 2016-08-04 | Completed | Script for GUI
24 | Attach data disk with standard or premium storage | Parameters List | Add-DataDiskToVM.ps1 | SavindraSingh | Through Cloud | 2016-08-02 | 2016-08-02 | 2016-08-08 | Completed
25 | Add AD DS role & promote the server as "additional DC" | Parameters List | Create-AdditionalDC.ps1 | Bhaskar | Through Cloud | 2016-07-21 | 2016-07-25 | 2016-08-04 | Script-Ready
26 | Add AD DS role & promote the server as "first DC" in forest | Parameters List | Create-DomainController.ps1 | Bhaskar | Through Cloud | 2016-07-26 | 2016-07-28 | 2016-08-05 | Script-Ready
27 | Attach static IP to Virtual Machine | Parameters List | Attach-StaticIPToVM.ps1 | Bhaskar | Through Cloud | 2016-08-03 | 2016-08-04 | 2016-08-04 | Script-Ready

## Task-SubTasks
Item. No. | Main Task | Sub-Tasks | Script Name | Script Details | Owner Name | Script Target | Start Date | Expected end date | Actual Completion Date | Status | Diva Sprint | DIVA readyness | Req for UI is available ?
1 | AZURE BACKUP SETUP - STANDARD - Setup(Azure VM) | Create Backup Vault | Create-AzureRMBackupVault.ps1 | Script | SavindraSingh | Cloud | 2016-05-16 | 2016-06-03 | 2016-06-02 | Script-Ready | Diva 2.0 (9/23) | Yes
|  | Installing MARS Agent | Install-BackupAgent.PS1 | Script | Bhaskar | Cloud | 2016-08-16 | 2016-08-20 |  | Script-Ready | Diva 2.0 (9/23)
|  | Register Protected Server | Register-ServerForBackup.ps1 | Script | Bhaskar | Cloud | 2016-08-16 | 2016-08-20 |  | Script-Ready | Diva 2.0 (9/23)
|  | Apply backup policies | Configure-BackupPolicy.ps1 | Script | Bhaskar | Cloud | 2016-08-16 | 2016-08-20 |  | Script-Ready | Diva 2.0 (9/23)
| AZURE BACKUP SETUP - PREMIUM - Setup(Azure VM) | Pre-Requisites for MABS | Pre-ReqCheck.ps1 | Script | Bhaskar | Cloud |  |  |  |  | Diva 2.0 (9/23)
|  | Installing MABS | NA | Manual | NA | Cloud | NA | NA | NA | NA | Diva 2.0 (9/23) | Manual steps
|  | Adding Disk Pool | NA | Manual | NA | Cloud |  |  |  | NA | Diva 2.0 (9/23)
|  | Pushing DPM Agent | NA | Manual | [5 empty] | NA | Diva 2.0 (9/23)
|  | Configure Backup Job/Policy | Create-ProtectionGrpStandalone.ps1 | Script | SavindraSingh/Bhaskar | Cloud | 2016-08-16 | 2016-08-17 | 2016-08-16 | Script-Ready | Diva 2.0 (9/23)
| Azure VM Backup | Create Backup Vault | Create-AzureRMBackupVault.ps1 | Script | Savindra Singh | Cloud |  |  |  | Script-Ready | Diva 2.0 (9/23)
|  | Backup Azure VM and apply parameters | Backup-AzureVM.ps1 | Script | Savindra Singh | Cloud | 2016-08-23 | 2016-09-08 |  | Script-Ready | Diva 2.0 (9/23)
2 | Azure Site Recovery (ASR) Setup | Setup Azure Network (Optional) | Create-AzureRMVNetFromTemplate.ps1 | Script | SavindraSingh | Cloud | 2016-05-16 | 2016-06-03 | 2016-06-02 | Script-Ready | Diva 2.1 (10/10) | Yes | Yes | Y
|  | Setup Azure Storage Account | Create-AzureRMStorageAccountFromTemplate.ps1 | Script | SavindraSingh | Cloud | 2016-05-26 | 2016-06-03 | 2016-06-03 | Script-Ready | Diva 2.1 (10/10) | No | Yes | Y
|  | Setup Azure recovery services vault | Create-AzureRMBackupVault.ps1 | Script | SavindraSingh | Cloud | 2016-05-16 | 2016-06-03 | 2016-06-02 | Script-Ready | Diva 2.1 (10/10) | Yes | Yes | Y
|  | Configure protection goals | NA | Manual | Bhaskar | On-Premise | NA | NA | NA | NA | Diva 2.1 (10/10) | Manual steps | NA | NA
|  | Enable replication | NA | Manual | Bhaskar | On-Premise | NA | NA | NA | NA | Diva 2.1 (10/10) | Manual steps | NA | NA
3 | Express Route Setup (VPN Tunnel)- Setup - Azure virtual network setup | Create VNET | Create-AzureRMVNetFromTemplate.ps1 | Script | SavindraSingh | Cloud | 2016-05-16 | 2016-06-03 | 2016-06-02 | Script-Ready | Diva 2.0 (9/23) | Yes | Yes | Y
Add IP address space
Create subnets (backend, frontend & gatewaysubnet)
|  | Create NSG and Apply NSG Rules | Create-NSGAndConfigureRules.ps1 | Script | Bhaskar | Cloud | 2016-07-21 | 2016-07-22 | 2016-07-22 | Script-Ready | Diva 2.0 (9/23) |  | Yes | Y
|  | Map NSG to subnet | Attach-NSGToSubnet.ps1 | Script | Bhaskar | Cloud | 2016-07-20 | 2016-07-20 | 2016-07-20 | Script-Ready | Diva 2.0 (9/23) |  |  | Y
|  | (OR) Map NSG to VM | Attach-NSGToVM.ps1 | Script | Bhaskar | Cloud | 2016-07-20 | 2016-07-20 | 2016-07-20 | Script-Ready | Diva 2.0 (9/23) |  | Yes | Y
|  | Add local area network (Hybrid) | Configure-HybridNetwork.ps1 | Script | Bhaskar | Cloud | 2016-07-25 | 2016-07-28 | 2016-07-28 | Script-Ready | Diva 2.0 (9/23) |  | Yes | Y
Create gateway for local area network (Hybrid)
|  | Update NSG with Rules as per customer | Update-NSGGroup.ps1 | Script | Bhaskar | Cloud | 2016-08-25 | 2016-08-29 | 2016-08-29 | Script-Ready | Diva 2.0 (9/23) |  | No | Y
4 | On-Premise Server Migration to Azure - Setup - AD Setup (Hybrid) | Create Azure VM in backend subnet (2008R2/2012 R2/2016) | Create-ARMVMFromGalleryImage.ps1 | Script | Bhaskar | Cloud | 2016-07-04 | 2016-07-05 | 2016-07-05 | Script-Ready | Diva 2.0 (9/23) |  | Yes | Y
|  | Add the VM to existing domain as member server | Add-AzureVMToDomain.ps1 | Script | Bhaskar | Cloud | 2016-07-19 | 2016-07-19 | 2016-07-19 | Script-Ready | Diva 2.0 (9/23) |  | Yes | Y
|  | Add AD DS role & promote the server as "additional DC" | Create-AdditionalDC.ps1 | Script | Bhaskar | Cloud | 2016-07-21 | 2016-07-25 | 2016-08-04 | Script-Ready | Diva 2.0 (9/23) |  | Yes | Y
|  | Verify Active Directory health and replication | NA | Manual | NA | On-Premise | NA | NA | NA | NA | Diva 2.0 (9/23) |  | NA | NA
5 | On-Premise Server Migration to Azure - Setup - AD Setup (only Azure) | Create Azure VM in backend subnet (2008R2/2012 R2/2016) | Create-ARMVMFromGalleryImage.ps1 | Script | Bhaskar | Cloud | 2016-07-04 | 2016-07-05 | 2016-07-05 | Script-Ready | Diva 2.0 (9/23) |  | Yes | Y
|  | Add AD DS role & promote the server as "first DC" in forest | Create-DomainController.ps1 | Script | Bhaskar | Cloud | 2016-07-26 | 2016-07-28 | 2016-08-05 | Script-Ready | Diva 2.0 (9/23) |  | Yes | Y
|  | Attach static IP to Virtual Machine | Attach-StaticIPToVM.ps1 | Script | Bhaskar | Cloud | 2016-08-03 | 2016-08-04 | 2016-08-04 | Script-Ready | Diva 2.0 (9/23) |  | Yes | Y
|  | Verify Active Directory health | NA | Manual | NA | On-Premise | NA | NA | NA | NA | Diva 2.0 (9/23) |  | NA | NA
6 | On-Premise Server Migration to Azure - Setup - AD Migration (Lift & Shift) | Take VM snapshot from On-premises | NA | Manual | NA | On-Premise | NA | NA | NA | NA | Diva 2.0 (9/23) |  | NA | NA
Convert the VM snapshot to VHD format (if required)
Copy the VHD to Azure storage
|  | Create OS disk from copied VHD | Create-ImageFromVHD.ps1 | Manual | Bhaskar | Manual | NA | NA | NA | NA | Diva 2.0 (9/23) | On hold due to some issue with image after processing |  | NA
|  | Snip up Azure VM in Backend Subnet | Create-ARMVMFromCustomImage.ps1 | Script | Bhaskar | Cloud | 2016-07-05 | 2016-07-06 | 2016-07-06 | Script-Ready | Diva 2.0 (9/23) |  | Yes | Y
|  | Verify Active Directory health | NA | Manual | NA | On-Premise | NA | NA | NA | NA | Diva 2.0 (9/23) |  | NA | NA
7 | On-Premise File Server Migration to Azure - Setup or Migrate - Create VM and Network | Create or configure VNET | Create-AzureRMVNetFromTemplate.ps1 | Script | SavindraSingh | Cloud | 2016-05-16 | 2016-06-03 | 2016-06-02 | Script-Ready | Diva 2.0 (9/23) |  | Yes | Y
|  | Create VM | Create-ARMVMFromGalleryImage.ps1 | Script | Bhaskar | Cloud | 2016-07-04 | 2016-07-05 | 2016-07-05 | Script-Ready | Diva 2.0 (9/23) |  | Yes | Y
|  | Domian join server to AD | Add-AzureVMToDomain.ps1 | Script | Bhaskar | Cloud | 2016-07-19 | 2016-07-19 | 2016-07-19 | Script-Ready | Diva 2.0 (9/23) |  | Yes | Y
|  | Create user with minimal privileage | NA | NA | SavindraSingh | NA | NA | NA | NA | NA | Diva 2.0 (9/23) | This was required in classic portal. Not required now | NA | NA
|  | Attach data disk with standard or premium storage | Add-DataDiskToVM.ps1 | Script | SavindraSingh | Cloud | 2016-08-02 | 2016-08-02 | 2016-08-08 | Script-Ready | Diva 2.0 (9/23) |  | Yes | Y
|  | Install file server role | NA | NA | SavindraSingh | NA | NA | NA |  | NA | Diva 2.0 (9/23) |  |  | NA
|  | Install latest patches | NA | Manual | NA | Cloud | NA | NA | NA | NA | Diva 2.0 (9/23) |  | Na | NA
|  | Configure LB, LB Rules and NATing | Configure-LBRulesAndNATing.ps1 | Script | Bhaskar | Cloud | 2016-08-01 | 2016-08-03 | 2016-08-03 | Script-Ready | Diva 2.0 (9/23) |  | Yes | Y
|  | Configure NSG settings (for VM) | Attach-NSGToVM.ps1 | Script | Bhaskar | Cloud | 2016-07-20 | 2016-07-20 | 2016-07-20 | Script-Ready | Diva 2.0 (9/23) |  | Yes | Y
|  | Configure firewall/endpont settings | NA | Manual | NA | Cloud | NA | NA | NA | NA | Diva 2.0 (9/23) |  | NA | NA
8 | On-Premise File Server Migration to Azure - Setup or Migrate - Migrate Data | Create file share folder and enable read/write permissions & Provide any advanced user setting on folder or server (if applicable) | Create-FileShareAndSetPermissions.ps1 | Manual | SavindraSingh | Cloud | 2016-08-08 | 2016-08-09 |  | Script-Ready | Diva 2.0 (9/23) |  |  | NA
|  | Use robocopy or other mode to migrate data to server shared folder | NA | Manual | NA | On-Premise | NA | NA | NA | NA | Diva 2.0 (9/23) |  | NA | NA
9 | On-Premise File Server Migration to Azure - Setup or Migrate - Initial Test | Test share is accessible in network | NA | Manual | NA | On-Premise | NA | NA | NA | NA | Diva 2.0 (9/23) |  | NA | NA
|  | Validate data size | NA | Manual | NA | On-Premise | NA | NA | NA | NA | Diva 2.0 (9/23) |  | NA | NA
10 | On-Premise Application Server Migration to Azure - Setup/Migrate | Create or Configure Vnet | Create-AzureRMVNetFromTemplate.ps1 | Script | SavindraSingh | Cloud | 2016-05-16 | 2016-06-03 | 2016-06-02 | Script-Ready | Diva 2.1 (10/10)
|  | Create VM | Create-ARMVMFromGalleryImage.ps1 | Script | Bhaskar | Cloud | 2016-07-04 | 2016-07-05 | 2016-07-05 | Script-Ready | Diva 2.1 (10/10)
|  | Domian join server to AD | Add-AzureVMToDomain.ps1 | Script | Bhaskar | Cloud | 2016-07-19 | 2016-07-19 | 2016-07-19 | Script-Ready | Diva 2.1 (10/10)
|  | Configure endpoints | NA | Script | NA | NA | NA | NA | NA | NA | Diva 2.1 (10/10)
|  | Configure LB, LB Rules and NATing | Configure-LBRulesAndNATing.ps1 | Script | Bhaskar | Cloud | 2016-07-01 | 2016-08-03 | 2016-08-03 | Script-Ready | Diva 2.1 (10/10) |  | Yes
|  | Configure NSG settings (for VM) | Attach-NSGToVM.ps1 | Script | Bhaskar | Cloud | 2016-07-20 | 2016-07-20 | 2016-07-20 | Script-Ready | Diva 2.1 (10/10)
|  | Configure firewall settings (Azure VM) | Configure-FirewallSettingsInVM.ps1 | Script | Bhaskar | Cloud | 2016-08-04 | 2016-08-05 | 2016-08-02 | Script-Ready | Diva 2.1 (10/10)
|  | Patch VM | NA | Manual | NA | Cloud | NA | NA | NA | NA | Diva 2.1 (10/10)
| On-Premise Application Server Migration to Azure - Setup/Migrate - Install role and softwares/SDKs | Install WebServer Role | Install-WebServerRoleOnRMVM.ps1 | Script | SavindraSingh | Cloud | 2016-09-12 | 2016-09-17 | 2016-09-24 | Script-Ready | Diva 2.1 (10/10)
|  | Install WebServer Role Features | [8 empty] | Diva 2.1 (10/10)
|  | Install necessary softwares | NA | Manual | NA | Cloud | NA | NA | NA | NA | Diva 2.1 (10/10)
| On-Premise Application Server Migration to Azure - Setup/Migrate - Create website and configure application | Configure Application pool settings | Export-IISApplicationPoolSettings.ps1 / Import-IISApplicationPoolSettings.ps1 | Script | SavindraSingh | Cloud | 2016-09-18 | 2016-09-22 | 2016-09-27 | Script-Ready | Diva 2.1 (10/10)
|  | Package up websites | NA | Manual | NA | On-Premise | NA | NA | NA | NA | Diva 2.1 (10/10)
|  | Copy package to Designation Server | NA | Manual | NA | On-Premise | NA | NA | NA | NA | Diva 2.1 (10/10)
|  | Extract Zip files for WebSites | NA | Manual | NA | On-Premise | NA | NA | NA | NA | Diva 2.1 (10/10)
|  | Configure websites and IIS | Export-IISWebSites.ps1 / Import-IISWebsites.ps1 | Script | SavindraSingh | Cloud | 2016-09-23 | 2016-09-26 | 2016-09-27 | Script-Ready | Diva 2.1 (10/10)
|  | Configure application bindings, settings and other dependency settings | [8 empty] | Diva 2.1 (10/10)
|  | Restart IIS | Restart-IISServices.ps1 | Script | SavindraSingh | Cloud | 2016-08-29 | 2016-08-30 | 2016-09-04 | Script-Ready | Diva 2.1 (10/10)
| On-Premise Application Server Migration to Azure - Setup/Migrate - Prepare Azure environment and db readiness | Create or use existing Vnet | Create-AzureRMVNetFromTemplate.ps1 | Script | SavindraSingh | Cloud | 2016-06-16 | 2016-06-03 | 2016-06-02 | Script-Ready | Diva 2.1 (10/10)
|  | Backup existing server data and move to Cloud location | NA | Manual | NA | On-Premise | NA | NA | NA | NA | Diva 2.1 (10/10)
|  | Fix any changes are required as per SQL version in cloud | NA | Manual | Bhaskar | Cloud | 2016-08-08 | 2016-08-10 |  | NA | Diva 2.1 (10/10)
|  | Provision VM with right SKU | Create-ARMVMFromGalleryImage.ps1 | Script | Bhaskar | Cloud | 2016-07-04 | 2016-07-05 | 2016-07-05 | Script-Ready | Diva 2.1 (10/10)
|  | Create database or restore with backed up data | Create-DatabaseAndRestoreData.ps1 | Script | Bhaskar | Cloud | 2016-08-11 | 2016-08-16 | 2016-08-16 | Script-Ready | Diva 2.1 (10/10)
|  | Domain join the server | Add-AzureVMToDomain.ps1 | Script | Bhaskar | Cloud | 2016-07-19 | 2016-07-19 | 2016-07-19 | Script-Ready | Diva 2.1 (10/10)
| On-Premise Application Server Migration to Azure - Setup/Migrate - Migrate Compatible SQL Server database to SQL Database | Configure Security and user groups to database | Configure-DBSecurityAndUserAccess.ps1 | Manual/Script | Bhaskar | NA | 2016-08-17 | 2016-08-19 |  | Script-Ready | Diva 2.1 (10/10)
|  | Configure admin settings like job, firewall and ports | Configure-FirewallSettingsInVM.ps1 | Script | Bhaskar | Cloud | 2016-08-04 | 2016-08-05 | 2016-08-02 | Script-Ready | Diva 2.1 (10/10)
| On-Premise Application Server Migration to Azure - Setup/Migrate - Enable geo replication (Optional) | Configure geo redundancy for high available db design | Need More Information | Script | Bindu | Cloud | 2016-07-25 | 2016-07-26 | 2016-07-29 | Script-Ready | Diva 2.1 (10/10)
| On-Premise Application Server Migration to Azure - Setup/Migrate - Update Application settings | Get the Azure VM IP or DNS and updated the connections accordingly | Get-VMConnectionDetails.ps1 | Script | Bhaskar | Cloud | 2016-09-14 | 2016-09-14 | 2016-09-14 | Script-Ready | Diva 2.1 (10/10)
| On-Premise Application Server Migration to Azure - Setup/Migrate - Initial Test | Test Default website | Test-DefaultWebsite.ps1 | Script | Bhaskar | Cloud | 2016-09-12 | 2016-09-13 | 2016-09-13 | Script-Ready | Diva 2.1 (10/10)
|  | Verify connectivity to SQL Server from tools or applications | Test-SQLConnectionExtension.ps1 | Script | Bhaskar | Cloud | 2016-09-15 | 2016-09-16 | 2016-09-16 | Script-Ready | Diva 2.1 (10/10)
| On-Premise Application Server Migration to Azure - Setup/Migrate - UAT | Perform UAT for each website and applications | Need More Information | Manual | Bhaskar | Cloud |  |  |  | Not-Started | Diva 2.1 (10/10)
|  | Perform UAT for each SQL Database | Need More Information | Manual | Bhaskar | Cloud |  |  |  | Not-Started | Diva 2.1 (10/10)
11 | Network Setup - Setup - Create VNET | Create VNET | Create-AzureRMVNetFromTemplate.ps1 | Script | SavindraSingh | Cloud | 2016-06-16 | 2016-06-03 | 2016-06-02 | Script-Ready | Diva 2.0 (9/23) |  | Yes | Y
|  | Add local area network (Hybrid) | Configure-HybridNetwork.ps1 | Script | Bhaskar | Cloud | 2016-07-25 | 2016-07-28 | 2016-07-28 | Script-Ready | Diva 2.0 (9/23) |  | Yes | Y
Create Gateway
Create VPN/Peering
12 | Azure REST API Script | Adding the Application to Azure AD | Add-ApplicationToAd.ps1 | Script | Bhaskar | Cloud | 2016-08-29 | 2016-08-29 | 2016-08-29 | Script-Ready | Diva 2.0 (9/23) |  |  | NA
Note on D44: SavindraSingh Shahoo: Create user with only Domain Users group membership. https://mshiyas.wordpress.com/tag/file-server-migration-to-azure-vm/
Note on D45: SavindraSingh Shahoo: https://gallery.technet.microsoft.com/scriptcenter/Add-a-new-data-disk-to-an-9f4573c7
Note on C50: SavindraSingh Shahoo: Not applicable for ARM mode
Note on C58: SavindraSingh Shahoo: NOT Applicable for ARM mode

## AzureTasks Tags (hidden)
SL # | TASK NAME | INPUT PARAMETERS | SCRIPT FILE NAME | MANDATORY | Source | TAG | FIELD TYPE | VALUES | SCHEDULES | GLOBAL OR CUSTOMER
1 | Create Backup Vault | ClientID | Create-AzureRMBackupVault.ps1 | Yes |  | ClientID | Textbox | Auto generated ClientID
|  | AzureUserName |  | Yes |  | AzureUserName | Textbox
|  | AzurePassword |  | Yes |  | AzurePassword | Textbox
|  | AzureSubscriptionID |  | Yes |  | AzureSubscriptionID | Textbox
|  | Location |  | Yes | Dropdown List | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes | Script | ResourceGroupName | Drop Down | List of available resource groups through script
|  | StorageType |  | Yes | Dropdown List | StorageType | Drop Down | GeoRedundant, LocallyRedundant
|  | VaultName |  | Yes |  | VaultName | Textbox
2 | Create Vnet (From Template) | ClientID | Create-AzureRMVNetFromTemplate.ps1 | Yes |  | ClientID | Textbox | Auto generated ClientID
|  | AzureUserName |  | Yes |  | AzureUserName | Textbox
|  | AzurePassword |  | Yes |  | AzurePassword | Textbox
|  | AzureSubscriptionID |  | Yes |  | AzureSubscriptionID | Textbox
|  | Location |  | Yes |  | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes |  | ResourceGroupName | Drop Down | List of available resource groups through script
|  | DeploymentName |  | No |  | DeploymentName | Textbox | Random value
|  | TemplateJSONPath |  | Yes |  | TemplateJSONPath | Textbox | Static Path
|  | ParameterJSONPath |  | Yes |  | ParameterJSONPath | Textbox | Static Path
|  | VNetName |  | Yes |  | VNetName | Textbox
|  | vnetAddressPrefix |  | Yes |  | vnetAddressPrefix | Textbox (IP Address) | Example: 10.0.0.0/16
|  | subnet1Prefix |  | Yes |  | subnet1Prefix | Textbox (IP Address) | Example: 10.0.0.0/24
|  | subnet2Prefix |  | Yes |  | subnet2Prefix | Textbox (IP Address) | Example: 10.0.0.0/24
|  | GatewayPrefix |  | Yes |  | GatewayPrefix | Textbox (IP Address) | Example: 10.0.0.0/26
3 | Create Backup Policy | WorkHourBandwidth | Configure-BackupPolicy.ps1 | No |  | WorkHourBandwidth | Textbox | Integer
|  | NonWorkHourBandwidth |  | No |  | NonWorkHourBandwidth | Textbox | Integer
|  | DaysOfWeek |  | Yes |  | DaysOfWeek | Check boxes | Monday, Tuesday,…,Sunday
|  | TimesOfDay |  | Yes |  | TimesOfDay | Textbox (Time) | HH:MM (time value)
|  | RetentionDays |  | Yes |  | RetentionDays | Textbox | Integer
|  | Exclude |  | No |  | Exclude | Multiline Textbox | File/folder Paths
|  | Include |  | Yes |  | Include | Multiline Textbox | File/folder Paths
4 | Create ARM VM (From Gallery Image) | AzureUserName | Create-ARMVMFromGalleryImage.ps1 | Yes |  | AzureUserName | Textbox
|  | AzurePassword |  | Yes |  | AzurePassword | Textbox
|  | AzureSubscriptionID |  | Yes |  | AzureSubscriptionID | Textbox
|  | Location |  | Yes |  | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes | Script (Drop Down) | ResourceGroupName | Drop Down | List of available resource groups through script
|  | DeploymentName |  | No | Random/Custom | DeploymentName | Textbox
|  | TemplateJSONPath |  | Yes | Default Value | TemplateJSONPath | Textbox
|  | ParameterJSONPath |  | Yes | Default Value | ParameterJSONPath | Textbox
|  | StorageAccountName |  | Yes |  | StorageAccountName | Textbox
|  | VMName |  | Yes |  | VMName | Textbox
|  | VMSize |  | Yes | Script (Drop Down) | VMSize | Drop Down | List of VM Sizes (Script)
|  | VNETName |  | Yes | Script (Drop Down) | VNETName | Drop Down | List of Vnets (available)
|  | SubnetName |  | Yes | Script (Drop Down) | SubnetName | Drop Down | List of Subnets (Available)
|  | VMImage |  | Yes | Script (Drop Down) | VMImage | Drop Down | List of available Images
|  | PublicIP |  | No |  | PublicIP | Check boxes | Yes, No (boolean value)
|  | VMUserName |  | Yes |  | VMUserName | Textbox
|  | VMUserPassword |  | Yes |  | VMUserPassword | Textbox
5 | Create ARM VM (From Custom VHD) | AzureUserName | Create-ARMVMFromCustomImage.ps1 | Yes |  | AzureUserName | Textbox
|  | AzurePassword |  | Yes |  | AzurePassword | Textbox
|  | AzureSubscriptionID |  | Yes |  | AzureSubscriptionID | Textbox
|  | Location |  | Yes |  | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes | Script (Drop Down) | ResourceGroupName | Drop Down | List of available resource groups (Script)
|  | DeploymentName |  | No | Random/Custom | DeploymentName | Textbox
|  | TemplateJSONPath |  | Yes | Default Value | TemplateJSONPath | Textbox
|  | ParameterJSONPath |  | Yes | Default Value | ParameterJSONPath | Textbox
|  | StorageAccountName |  | Yes |  | StorageAccountName | Textbox
|  | VMName |  | Yes |  | VMName | Textbox
|  | VMSize |  | Yes | Script (Drop Down) | VMSize | Drop Down | List of VM Sizes allowed values (Script)
|  | VNETName |  | Yes | Script (Drop Down) | VNETName | Drop Down | List of Vnets (Script)
|  | SubnetName |  | Yes | Script (Drop Down) | SubnetName | Drop Down | List of Subnets (Script)
|  | OSDiskURIPath |  | Yes |  | OSDiskURIPath | Textbox | Validate URL format
|  | PublicIP |  | No |  | PublicIP | Check boxes | Yes, No (boolean value)
|  | VMUserName |  | Yes |  | VMUserName | Textbox
|  | VMUserPassword |  | Yes |  | VMUserPassword | Textbox | Password field
6 | Get List of Resource Groups (for dropdown) | AzureUserName | Get-ListOfResourceGroupNames.ps1 | Yes |  | AzureUserName | Textbox
|  | AzurePassword |  | Yes |  | AzurePassword | Textbox
|  | AzureSubscriptionID |  | Yes |  | AzureSubscriptionID | Textbox
7 | Get List of Virtual Machines | AzureUserName | Get-ListOfVirtualMachines.ps1 | Yes |  | AzureUserName | Textbox
|  | AzurePassword |  | Yes |  | AzurePassword | Textbox
|  | AzureSubscriptionID |  | Yes |  | AzureSubscriptionID | Textbox
8 | Get List of Virtual Networks | AzureUserName | Get-ListOfVNets.ps1 | Yes |  | AzureUserName | Textbox
|  | AzurePassword |  | Yes |  | AzurePassword | Textbox
|  | AzureSubscriptionID |  | Yes |  | AzureSubscriptionID | Textbox
9 | Get List of Subnets from Vnet | AzureUserName | Get-ListOfVNetSubnets.ps1 | Yes |  | AzureUserName | Textbox
|  | AzurePassword |  | Yes |  | AzurePassword | Textbox
|  | AzureSubscriptionID |  | Yes |  | AzureSubscriptionID | Textbox
|  | ResourceGroupName |  | Yes | Script (Drop Down) | ResourceGroupName | Drop Down | List of available resource groups (Script)
|  | VNetName |  | Yes | Script (Drop Down) | VNetName | Drop Down
10 | Get List of VM Sizes (from Location) | AzureUserName | Get-ListOfVMSizes.txt | Yes |  | AzureUserName | Textbox
|  | AzurePassword |  | Yes |  | AzurePassword | Textbox
|  | AzureSubscriptionID |  | Yes |  | AzureSubscriptionID | Textbox
|  | Location |  | Yes | Dropdown List | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
11 | Create Azure RM Storage Account (From Template) | AzureUserName | Create-AzureRMStorageAccountFromTemplate.ps1 | Yes |  | AzureUserName | Textbox
|  | AzurePassword |  | Yes |  | AzurePassword | Textbox
|  | AzureSubscriptionID |  | Yes |  | AzureSubscriptionID | Textbox
|  | Location |  | Yes | Dropdown List | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes | Script (Drop Down) | ResourceGroupName | Drop Down | List of available resource groups (Script)
|  | DeploymentName |  | No | Random/Custom | DeploymentName | Textbox
|  | TemplateJSONPath |  | Yes | Default Value | TemplateJSONPath | Textbox
|  | ParameterJSONPath |  | Yes | Default Value | ParameterJSONPath | Textbox
|  | PerformanceTear |  | Yes | Dropdown List | PerformanceTear | Drop Down | Standard_LRS, Standard_GRS, Standard_ZRS, Premium_LRS
|  | StorageAccountName |  | Yes |  | StorageAccountName | Textbox
12 | Backup Azure IIS VM | AzureUserName | Backup-AzureIISVM.ps1 | Yes |  | AzureUserName | Textbox
|  | AzurePassword |  | Yes |  | AzurePassword | Textbox
|  | AzureSubscriptionID |  | Yes |  | AzureSubscriptionID | Textbox
|  | Location |  | Yes | Dropdown List | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes | Script (Drop Down) | ResourceGroupName | Drop Down | List of available resource groups (Script)
|  | RSVaultName |  | Yes |  | RSVaultName | Textbox
|  | BackupStorageRedundancy |  | Yes |  | BackupStorageRedundancy | Drop Down | LocallyRedundant, GeoRedundant
|  | VMToBackup |  | Yes |  | VMToBackup | Textbox
13 | Configure MABS (Azure Backup Server)

## Locations (hidden)
AZURE REGION | LOCATION | Sunday
Central US | Iowa | Monday
East US | Virginia | Tuesday
East US 2 | Virginia | Wednesday
US Gov Iowa | Iowa | Thursday
US Gov Virginia | Virginia | Friday
North Central US | Illinois | Saturday
South Central US | Texas
West US | California
North Europe | Ireland
West Europe | Netherlands
East Asia | Hong Kong
Southeast Asia | Singapore
Japan East | Tokyo, Saitama
Japan West | Osaka
Brazil South | Sao Paulo State
Australia East | New South Wales
Australia Southeast | Victoria
Central India | Pune
South India | Chennai
West India | Mumbai
China East | Shanghai
China North | Beijing
Canada Central | Toronto
Canada East | Quebec City

## Create-AzureRMBackupVault
SL # | TASK NAME | INPUT PARAMETERS | SCRIPT FILE NAME | MANDATORY | TAG | FIELD TYPE | VALUES
1 | Create Backup Vault | ClientID | Create-AzureRMBackupVault.ps1 | Yes | ClientID | Textbox | Auto generated ClientID
|  | AzureUserName |  | Yes | AzureUserName | Textbox
|  | AzurePassword |  | Yes | AzurePassword | Textbox | Password field
|  | AzureSubscriptionID |  | Yes | AzureSubscriptionID | Textbox | GUID
|  | Location |  | Yes | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes | ResourceGroupName | Drop Down | List of available resource groups through script
|  | StorageType |  | Yes | StorageType | Drop Down | GeoRedundant, LocallyRedundant
|  | VaultName |  | Yes | VaultName | Textbox

## Create-AzureRMVNetFromTemplate
SL # | TASK NAME | INPUT PARAMETERS | SCRIPT FILE NAME | MANDATORY | TAG | FIELD TYPE | VALUES
1 | Create Vnet (From Template) | ClientID | Create-AzureRMVNetFromTemplate.ps1 | Yes | ClientID | Textbox | Auto generated ClientID
|  | AzureUserName |  | Yes | AzureUserName | Textbox
|  | AzurePassword |  | Yes | AzurePassword | Textbox | Password field
|  | AzureSubscriptionID |  | Yes | AzureSubscriptionID | Textbox | GUID
|  | Location |  | Yes | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes | ResourceGroupName | Drop Down | List of available resource groups through script
|  | DeploymentName |  | No | DeploymentName | Textbox | Random value
|  | TemplateJSONPath |  | Yes | TemplateJSONPath | Textbox | Static Path
|  | ParameterJSONPath |  | Yes | ParameterJSONPath | Textbox | Static Path
|  | VNetName |  | Yes | VNetName | Textbox
|  | vnetAddressPrefix |  | Yes | vnetAddressPrefix | Textbox (IP Address) | Example: 10.0.0.0/16
|  | subnet1Prefix |  | Yes | subnet1Prefix | Textbox (IP Address) | Example: 10.0.0.0/24
|  | subnet2Prefix |  | Yes | subnet2Prefix | Textbox (IP Address) | Example: 10.0.0.0/24
|  | GatewayPrefix |  | Yes | GatewayPrefix | Textbox (IP Address) | Example: 10.0.0.0/26

## Create-AzureRMStorageAccount
SL # | TASK NAME | INPUT PARAMETERS | SCRIPT FILE NAME | MANDATORY | TAG | FIELD TYPE | VALUES
1 | Create Azure RM Storage Account (From Template) | ClientID | Create-AzureRMStorageAccountFromTemplate.ps1 | Yes | ClientID | Textbox | Auto generated ClientID
|  | AzureUserName |  | Yes | AzureUserName | Textbox
|  | AzurePassword |  | Yes | AzurePassword | Textbox | Password field
|  | AzureSubscriptionID |  | Yes | AzureSubscriptionID | Textbox | GUID
|  | Location |  | Yes | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes | ResourceGroupName | Drop Down | List of available resource groups (Script)
|  | DeploymentName |  | No | DeploymentName | Textbox
|  | TemplateJSONPath |  | Yes | TemplateJSONPath | Textbox
|  | ParameterJSONPath |  | Yes | ParameterJSONPath | Textbox
|  | PerformanceTear |  | Yes | PerformanceTear | Drop Down | Standard_LRS, Standard_GRS, Standard_ZRS, Premium_LRS
|  | StorageAccountName |  | Yes | StorageAccountName | Textbox

## Create-NSGAndConfigureRules
SL # | TASK NAME | INPUT PARAMETERS | SCRIPT FILE NAME | MANDATORY | TAG | FIELD TYPE | VALUES
1 | Create NSG and Apply NSG Rules | ClientID | Create-NSGAndConfigureRules.ps1 | Yes | ClientID | Textbox | Auto generated ClientID
|  | AzureUserName |  | Yes | AzureUserName | Textbox
|  | AzurePassword |  | Yes | AzurePassword | Textbox | Password field
|  | AzureSubscriptionID |  | Yes | AzureSubscriptionID | Textbox | GUID
|  | Location |  | Yes | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes | ResourceGroupName | Drop Down | List of available resource groups through script
|  | NSGGroupName |  | Yes | NSGGroupName | Textbox
|  | RuleName |  | Yes | RuleName | Textbox
|  | SourceAddressPrefix |  | Yes | SourceAddressPrefix | Textbox (IP Address) | Example: 10.0.0.0/16
|  | SourcePortRange |  | Yes | SourcePortRange | Textbox | Integer value
|  | DestinationAddressPrefix |  | Yes | DestinationAddressPrefix | Textbox (IP Address) | Example: 10.0.0.0/16
|  | DestinationPortRange |  | Yes | SourcePortRange | Textbox | Integer value
|  | RuleAction |  | Yes | RuleAction | Drop Down | "Allow","Deny"
|  | Protocol |  | Yes | Protocol | Drop Down | "TCP","UDP","*"
|  | FlowDirection |  | Yes | FlowDirection | Drop Down | "Inbound","Outbound"
|  | Priority |  | Yes | Priority | Textbox | Integer (min 100)
Note on C11: SavindraSingh Shahoo: Discuss with us (me or Bhaskar) for more details.
Note on C13: SavindraSingh Shahoo: Discuss with us (me or Bhaskar) for more details.
Note on C17: SavindraSingh Shahoo: Discuss with us (me or Bhaskar) for more details.

## Attach-NSGToVM
SL # | TASK NAME | INPUT PARAMETERS | SCRIPT FILE NAME | MANDATORY | TAG | FIELD TYPE | VALUES
1 | Map NSG to VM | ClientID | Attach-NSGToVM.ps1 | Yes | ClientID | Textbox | Auto generated ClientID
|  | AzureUserName |  | Yes | AzureUserName | Textbox
|  | AzurePassword |  | Yes | AzurePassword | Textbox | Password field
|  | AzureSubscriptionID |  | Yes | AzureSubscriptionID | Textbox | GUID
|  | Location |  | Yes | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes | ResourceGroupName | Drop Down | List of available resource groups through script
|  | NSGGroup |  | Yes | NSGGroup | Textbox
|  | VMName |  | Yes | VMName | Textbox
|  | NICCardNames |  | Yes | NICCardNames | Textbox | Can accept multiple values (comma seperated)

## Configure-HybridNetwork
SL # | TASK NAME | INPUT PARAMETERS | SCRIPT FILE NAME | MANDATORY | TAG | FIELD TYPE | VALUES
1 | Add local area network (Hybrid) Create gateway for local area network (Hybrid) | ClientID | Configure-HybridNetwork.ps1 | Yes | ClientID | Textbox | Auto generated ClientID
|  | AzureUserName |  | Yes | AzureUserName | Textbox
|  | AzurePassword |  | Yes | AzurePassword | Textbox | Password field
|  | AzureSubscriptionID |  | Yes | AzureSubscriptionID | Textbox | GUID
|  | Location |  | Yes | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes | ResourceGroupName | Drop Down | List of available resource groups through script
|  | DeploymentName |  | Yes | DeploymentName | Textbox
|  | VNetName |  | Yes | VNetName | Textbox
|  | VNetGatewayName |  | Yes | VNetGatewayName | Textbox
|  | VNetGatewaySubnetPrefix |  | Yes | VNetGatewaySubnetPrefix | Textbox (IP Address) | Example: 10.0.0.0/16
|  | VNetGatewayPIPName |  | Yes | VNetGatewayPIPName | Textbox
|  | LocalNetworkName |  | Yes | LocalNetworkName | Textbox
|  | LocalNetGatewayName |  | Yes | LocalNetGatewayName | Textbox
|  | LocalNetAddressPrefix |  | Yes | LocalNetAddressPrefix | Textbox (IP Address) | Example: 10.0.0.0/16
|  | LocalNetVPNGatewayIP |  | Yes | LocalNetVPNGatewayIP | Textbox (IP Address) | Example: 10.0.0.0
|  | GatewayType |  | Yes | GatewayType | Drop Down | "VPN","ExpressRoute"
|  | VPNType |  | Yes | VPNType | Drop Down | "RouteBased","PolicyBased"
|  | GatewayTier |  | Yes | GatewayTier | Drop Down | "Basic","Standard","HighPerformance"
|  | SharedKey |  | Yes | SharedKey | Textbox
|  | ConnectionName |  | Yes | ConnectionName | Textbox
|  | CircuitName |  | Yes | CircuitName | Textbox
|  | ConnectionType |  | Yes | ConnectionType | Drop Down | "IPSec","ExpressRoute","VNet2VNet"
|  | TemplateJSONPath |  | Yes | TemplateJSONPath | Textbox | Static Path
|  | ParameterJSONPath |  | Yes | ParameterJSONPath | Textbox | Static Path
Note on C17: SavindraSingh Shahoo: Discuss with Bhaskar while desiging the form.

## Create-ARMVMFromGalleryImage
SL # | TASK NAME | INPUT PARAMETERS | SCRIPT FILE NAME | MANDATORY | TAG | FIELD TYPE | VALUES
1 | Create ARM VM (From Gallery Image) | ClientID | Create-ARMVMFromGalleryImage.ps1 | Yes | ClientID | Textbox | Auto generated ClientID
|  | AzureUserName |  | Yes | AzureUserName | Textbox
|  | AzurePassword |  | Yes | AzurePassword | Textbox | Password field
|  | AzureSubscriptionID |  | Yes | AzureSubscriptionID | Textbox | GUID
|  | Location |  | Yes | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes | ResourceGroupName | Drop Down | List of available resource groups through script
|  | AvailabilitySetName |  | Yes | AvailabilitySetName | Textbox
|  | DeploymentName |  | Yes | DeploymentName | Textbox
|  | TemplateJSONPath |  | Yes | TemplateJSONPath | Textbox
|  | ParameterJSONPath |  | Yes | ParameterJSONPath | Textbox
|  | StorageAccountName |  | Yes | StorageAccountName | Textbox
|  | VMName |  | Yes | VMName | Textbox
|  | VMSize |  | Yes | VMSize | Drop Down | List of VM Sizes (Script)
|  | VirtualNetworkName |  | Yes | VirtualNetworkName | Drop Down | List of Vnets (available)
|  | SubnetName |  | Yes | SubnetName | Drop Down | List of Subnets (Available)
|  | PublisherName |  | Yes | PublisherName | Drop Down | List of Publishers (Script) | Depends on Location as Input parameter
|  | OfferName |  | Yes | OfferName | Drop Down | List of Offers (Script)
|  | SKUName |  | Yes | SKUName | Drop Down | List of available Images
|  | DNSNameForPublicIP |  | Yes | DNSNameForPublicIP | Textbox | Yes, No (boolean value)
|  | AdminUserName |  | Yes | AdminUserName | Textbox
|  | AdminPassword |  | Yes | AdminPassword | Textbox

## Add-AzureVMToDomain
SL # | TASK NAME | INPUT PARAMETERS | SCRIPT FILE NAME | MANDATORY | TAG | FIELD TYPE | VALUES
1 | Add the VM to existing domain as member server | ClientID | Add-AzureVMToDomain.ps1 | Yes | ClientID | Textbox | Auto generated ClientID
|  | AzureUserName |  | Yes | AzureUserName | Textbox
|  | AzurePassword |  | Yes | AzurePassword | Textbox | Password field
|  | AzureSubscriptionID |  | Yes | AzureSubscriptionID | Textbox | GUID
|  | Location |  | Yes | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes | ResourceGroupName | Drop Down | List of available resource groups through script
|  | VMName |  | Yes | VMName | Textbox
|  | DomainName |  | Yes | DomainName | Textbox
|  | DomainUserName |  | Yes | DomainUserName | Textbox
|  | DomainUserPassword |  | Yes | DomainUserPassword | Password (textbox)
Note on C10: SavindraSingh Shahoo: Need to take domain name from above textbox values and append a '\' before the user name. (Disuss for more details)

## Create-ARMVMFromCustomImage
SL # | TASK NAME | INPUT PARAMETERS | SCRIPT FILE NAME | MANDATORY | TAG | FIELD TYPE | VALUES
1 | Create ARM VM (From Custom VHD) | ClientID | Create-ARMVMFromCustomImage.ps1 | Yes | ClientID | Textbox | Auto generated ClientID
|  | AzureUserName |  | Yes | AzureUserName | Textbox
|  | AzurePassword |  | Yes | AzurePassword | Textbox | Password field
|  | AzureSubscriptionID |  | Yes | AzureSubscriptionID | Textbox | GUID
|  | Location |  | Yes | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes | ResourceGroupName | Drop Down | List of available resource groups (Script)
|  | DeploymentName |  | No | DeploymentName | Textbox
|  | TemplateJSONPath |  | Yes | TemplateJSONPath | Textbox
|  | ParameterJSONPath |  | Yes | ParameterJSONPath | Textbox
|  | StorageAccountName |  | Yes | StorageAccountName | Textbox
|  | VMName |  | Yes | VMName | Textbox
|  | VMSize |  | Yes | VMSize | Drop Down | List of VM Sizes allowed values (Script)
|  | VirtualNetworkName |  | Yes | VirtualNetworkName | Drop Down | List of Vnets (Script)
|  | SubnetName |  | Yes | SubnetName | Drop Down | List of Subnets (Script)
|  | OSImageURI |  | Yes | OSImageURI | Textbox | Validate URL format
|  | DNSNameForPublicIP |  | No | DNSNameForPublicIP | Check boxes | Yes, No (boolean value)
|  | AdminUserName |  | Yes | AdminUserName | Textbox
|  | AdminPassword |  | Yes | AdminPassword | Textbox | Password field
|  | AvailabilitySetName |  | Yes | AvailabilitySetName | Drop Down | List of availability sets from Script
|  | OSType |  | Yes | OSType | Drop Down | "Windows","Linux"
Note on C20: SavindraSingh Shahoo: There should be one option in the drop-down to create new availability set and when that option is selected, it should show Textbox to enter new availability set.

## Backup-AzureVM
SL # | TASK NAME | INPUT PARAMETERS | SCRIPT FILE NAME | MANDATORY | TAG | FIELD TYPE | VALUES
1 | Backup Azure VM | ClientID | Backup-AzureVM.ps1 | Yes | ClientID | Textbox | Auto generated ClientID
|  | AzureUserName |  | Yes | AzureUserName | Textbox
|  | AzurePassword |  | Yes | AzurePassword | Textbox | Password field
|  | AzureSubscriptionID |  | Yes | AzureSubscriptionID | Textbox | GUID
|  | Location |  | Yes | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes | ResourceGroupName | Drop Down | List of available resource groups (Script)
|  | RSVaultName |  | Yes | RSVaultName | Drop Down | List of existing recovery services vaults
|  | BackupStorageRedundancy |  | Yes | BackupStorageRedundancy | Drop Down | LocallyRedundant, GeoRedundant
|  | VMToBackup |  | Yes | VMToBackup | Drop Down | List of existing VMs
|  | DaysOfWeek |  | Yes | DaysOfWeek | CheckBox | Sunday, Monday.. Saturday
|  | TimesOfDay |  | Yes | TimesOfDay | Drop Down | Only Time Values in multiples of 30 minutes
|  | ScheduleRunFrequency |  | Yes | ScheduleRunFrequency | Radio Button | Daily,Weekly
|  | VMBackupPolicyName |  | Yes | VMBackupPolicyName | Textbox | Name string for Policy name (Min 3 max 150 chars)
|  | EnableWeeklyRetentionSchedule |  | Yes | EnableWeeklyRetentionSchedule | CheckBox | Yes,No
|  | EnableMonthlyRetentionSchedule |  | Yes | EnableMonthlyRetentionSchedule | CheckBox | Yes,No
|  | EnableYearlyRetentionSchedule |  | Yes | EnableYearlyRetentionSchedule | CheckBox | Yes,No

## Add-DataDiskToVM
SL # | TASK NAME | INPUT PARAMETERS | SCRIPT FILE NAME | MANDATORY | TAG | FIELD TYPE | VALUES
1 | Attach data disk with standard or premium storage | ClientID | Add-DataDiskToVM.ps1 | Yes | ClientID | Textbox | Auto generated ClientID
|  | AzureUserName |  | Yes | AzureUserName | Textbox
|  | AzurePassword |  | Yes | AzurePassword | Textbox | Password field
|  | AzureSubscriptionID |  | Yes | AzureSubscriptionID | Textbox | GUID
|  | Location |  | Yes | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes | ResourceGroupName | Drop Down | List of available resource groups (Script)
|  | VMName |  | Yes | VMName | Drop Down | Select from existing list of VMs available under this subscription (through script)
|  | DiskName |  | Yes | DiskName | Textbox | Name to be given to Disk e.g. DD1 or DISK1 etc.
|  | DiskSizeInGB |  | Yes | DiskSizeInGB | Textbox or NumericUpDown | Min value 1 and max value 1023

## Create-AdditionalDC
SL # | TASK NAME | INPUT PARAMETERS | SCRIPT FILE NAME | MANDATORY | TAG | FIELD TYPE | VALUES
1 | Add AD DS role & promote the server as "additional DC" | ClientID | Create-AdditionalDC.ps1 | Yes | ClientID | Textbox | Auto generated ClientID
|  | AzureUserName |  | Yes | AzureUserName | Textbox
|  | AzurePassword |  | Yes | AzurePassword | Textbox | Password field
|  | AzureSubscriptionID |  | Yes | AzureSubscriptionID | Textbox | GUID
|  | Location |  | Yes | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes | ResourceGroupName | Drop Down | List of available resource groups (Script)
|  | VMName |  | Yes | VMName | Drop Down | List of available VMs through script
|  | DomainName |  | Yes | DomainName | Textbox | Name of the existing domain
|  | DomainAdmin |  | Yes | DomainAdmin | Textbox
|  | PasswordForDomainAdmin |  | Yes | PasswordForDomainAdmin | Textbox (Password)

## Create-DomainController
SL # | TASK NAME | INPUT PARAMETERS | SCRIPT FILE NAME | MANDATORY | TAG | FIELD TYPE | VALUES
1 | Add AD DS role & promote the server as "first DC" in forest | ClientID | Create-DomainController.ps1 | Yes | ClientID | Textbox | Auto generated ClientID
|  | AzureUserName |  | Yes | AzureUserName | Textbox
|  | AzurePassword |  | Yes | AzurePassword | Textbox | Password field
|  | AzureSubscriptionID |  | Yes | AzureSubscriptionID | Textbox | GUID
|  | Location |  | Yes | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes | ResourceGroupName | Drop Down | List of available resource groups (Script)
|  | VMName |  | Yes | VMName | Drop Down | List of available VMs through script
|  | DomainName |  | Yes | DomainName | Textbox | Name of the existing domain
|  | PasswordForDomainAdmin |  | Yes | PasswordForDomainAdmin | Textbox (Password)
|  | DomainNETBiosName |  | Yes | DomainNETBiosName | Textbox
|  | DomainMode |  | Yes | DomainMode | Drop Down | "Windows2008","Windows2012"

## Attach-StaticIPToVM
SL # | TASK NAME | INPUT PARAMETERS | SCRIPT FILE NAME | MANDATORY | TAG | FIELD TYPE | VALUES
1 |  | ClientID | Attach-StaticIPToVM.ps1 | Yes | ClientID | Textbox | Auto generated ClientID
|  | AzureUserName |  | Yes | AzureUserName | Textbox
|  | AzurePassword |  | Yes | AzurePassword | Textbox | Password field
|  | AzureSubscriptionID |  | Yes | AzureSubscriptionID | Textbox | GUID
|  | Location |  | Yes | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes | ResourceGroupName | Drop Down | List of available resource groups (Script)
|  | VMName |  | Yes | VMName | Drop Down | List of available VMs through script
|  | NICCardNames |  | Yes | NICCardNames | Drop Down | List of NIC cards on VM through script
|  | StaticIPAddress |  | Yes | StaticIPAddress | Textbox | Validate for a valid IP.

## Backup Vault - Standard
1 | Create Backup Vault | ClientID | Create-AzureRMBackupVault.ps1 | Yes |  | ClientID | Textbox | It has to come from Backend Code
|  | AzureUserName |  | Yes |  | AzureUserName | Textbox
|  | AzurePassword |  | Yes |  | AzurePassword | Textbox
|  | AzureSubscriptionID |  | Yes | Location | AzureSubscriptionID | Textbox
|  | ResourceGroupName |  | Yes | Script | ResourceGroupName | Drop Down | List of available resource groups through script
|  | Location |  | Yes | Dropdown List | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | StorageType |  | Yes | Dropdown List | StorageType | Drop Down | GeoRedundant, LocallyRedundant
|  | VaultName |  | Yes |  | VaultName | Textbox
2 | Install MARS Agent | ClientID | Install-BackupAgent.ps1 | yes |  | ClientID | Textbox | It has to come from Backend Code
|  | AzureUserName |  | Yes |  | AzureUserName | Textbox
|  | AzurePassword |  | Yes |  | AzurePassword | Textbox
|  | AzureSubscriptionID |  | Yes |  | AzureSubscriptionID | Textbox
|  | ResourceGroupName |  | Yes | Script | ResourceGroupName | Drop Down | List of available resource groups through script
|  | Location |  | Yes | Dropdown List | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | VMName |  | Yes | Dropdown List | VMName | Drop Down
3 | Register Protected Server | ClientID | Register-ServerForBackup.ps1 | Yes |  | ClientID |  | It has to come from Backend Code
|  | AzureUserName |  | Yes |  | AzureUserName | Textbox
|  | AzurePassword |  | Yes |  | AzurePassword | Textbox
|  | AzureSubscriptionID |  | Yes |  | AzureSubscriptionID | Textbox
|  | ResourceGroupName |  | Yes | Script | ResourceGroupName | Drop Down | List of available resource groups through script
|  | Location |  | Yes | Dropdown List | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | VmName |  | Yes | Dropdown List | VmName | Drop Down
|  | BackupVaultName |  | Yes | Dropdown List | BackupVaultName | Drop Down | List of available backup vaults
|  | StorageAccountName |  | Yes |  | StorageAccountName | Textbox
|  | Passphrase |  | Yes |  | Passphrase | Textbox | String of minimun of 17 characters
4 | Apply Backup Policy | ClientID | Configure-BackupPolicy.ps1 | Yes |  | ClientID |  | It has to come from Backend Code
|  | AzureUserName |  | Yes |  | AzureUserName | Textbox
|  | AzurePassword |  | Yes |  | AzurePassword | Textbox
|  | AzureSubscriptionID |  | Yes |  | AzureSubscriptionID | Textbox
|  | ResourceGroupName |  | Yes | Script | ResourceGroupName | Drop Down | List of available resource groups through script
|  | Location |  | Yes | Dropdown List | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | VMName |  | Yes | Dropdown List | VMName | Drop Down | List of Rgistered protected servers. Use the script 'Get-ListOfProductionServers' to get these servers.
|  | DaysOfWeek |  | Yes |  | DaysOfWeek | Check Boxes | Monday, Tuesday,…,Sunday
|  | TimesOfDay |  | Yes |  | TimesOfDay | Textbox | HH:MM (time value)
|  | Exclude |  | No |  | Exclude | Multiline Textbox | File/folder Paths
|  | Include |  | Yes |  | Include | Multiline Textbox | File/folder Paths
|  | RetentionDays |  | Yes |  | RetentionDays | Textbox | Integer
|  | NonWorkHourBandwidth |  | No |  | NonWorkHourBandwidth | Textbox | Integer
|  | WorkHourBandwidth |  | No |  | WorkHourBandwidth | Textbox | Integer

## Backup Vault - Premium
SL # | TASK NAME | INPUT PARAMETERS | SCRIPT FILE NAME | MANDATORY | TAG | FIELD TYPE | VALUES
1 | Pre-req Check | ClientID | Pre-ReqCheck.ps1 | Yes | ClientID | Textbox | Auto generated ClientID
|  | AzureUserName |  | Yes | AzureUserName | Textbox
|  | AzurePassword |  | Yes | AzurePassword | Textbox | Password field
|  | AzureSubscriptionID |  | Yes | AzureSubscriptionID | Textbox | GUID
|  | ResourceGroupName |  | Yes | ResourceGroupName | Drop Down | List of available resource groups through script
|  | Location |  | Yes | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | VMName |  | Yes | VMName | Drop Down | List of Virtual Machines

## Add-NSGToSubnet
SL # | TASK NAME | INPUT PARAMETERS | SCRIPT FILE NAME | MANDATORY | TAG | FIELD TYPE | VALUES
1 | Map NSG to Subnet | ClientID | Attach-NSGToSubnet.ps1 | Yes | ClientID | Textbox | Auto generated ClientID
|  | AzureUserName |  | Yes | AzureUserName | Textbox
|  | AzurePassword |  | Yes | AzurePassword | Textbox | Password field
|  | AzureSubscriptionID |  | Yes | AzureSubscriptionID | Textbox | GUID
|  | NSGGroup |  | Yes | NSGGroup | Drop Down | List of available Network Security Groups
|  | ResourceGroupName |  | Yes | ResourceGroupName | Drop Down | List of available resource groups through script
|  | VNetName |  | Yes | VNetName | Drop Down | List of Available Virtual Networks
|  | SubnetName |  | Yes | SubnetName | Drop Down | List of Available Subnets in Virtual Network

## Configure-LBrulesAndNAting
SL # | TASK NAME | INPUT PARAMETERS | SCRIPT FILE NAME | MANDATORY | TAG | FIELD TYPE | VALUES
1 | Configure LB, LB Rules and NATing | ClientID | Configure-LBRulesAndNATing.ps1 | Yes | ClientID | Textbox | Auto generated ClientID
|  | AzureUserName |  | Yes | AzureUserName | Textbox
|  | AzurePassword |  | Yes | AzurePassword | Textbox | Password field
|  | AzureSubscriptionID |  | Yes | AzureSubscriptionID | Textbox | GUID
|  | Location |  | Yes | Location | Drop Down | Central US, East US, East US 2, US Gov Iowa, US Gov Virginia, North Central US, South Central US, West US, North Europe, West Europe, East Asia, Southeast Asia, Japan East, Japan West, Brazil South, Australia East, Australia Southeast, Central India, South India, West India, China East, China North, Canada Central, Canada East,
|  | ResourceGroupName |  | Yes | ResourceGroupName | Drop Down | List of available resource groups through script
|  | LoadBalancerName |  | Yes | LoadBalancerName | Textbox
|  | LoadBalancerType |  | Yes | LoadBalancerType | Drop Down | Internal','Public'
|  | PublicIPAddressName |  | Yes | PublicIPAddressName | Textbox
|  | VirtualNetworkName |  | Yes | VirtualNetworkName | Drop Down | List of available virtual networks in case if Loadbalancer type is Internal
|  | SubnetName |  | Yes | SubnetName | Drop Down | List of available Subnets in case if Loadbalancer type is Internal
|  | IPAddressType |  | Yes | IPAddressType | Drop Down | Dynamic','Static'
|  | StaticIPAddress |  | Yes | StaticIPAddress | Textbox | IPAddress if IPAddress Type is Static
|  | ProbeName |  | Yes | ProbeName | Textbox
|  | ProbeProtocol |  | Yes | ProbeProtocol | Drop Down | Http','tcp'
|  | ProbePort |  | Yes | ProbePort | Textbox | Integer
|  | ProbePath |  | Yes | ProbePath | Textbox | Probe path if the probe protocol is http
|  | ProbeInterval |  | Yes | ProbeInterval | Textbox | Integer
|  | ProbeUnhealthythreshold |  | Yes | ProbeUnhealthythreshold | Textbox | Integer
|  | BackEndPoolName |  | Yes | BackEndPoolName | Textbox
|  | InboundNATRuleName |  | Yes | InboundNATRuleName | Textbox
|  | InboundProtocol |  | Yes | InboundProtocol | Drop Down | TCP','UDP'
|  | InboundPort |  | Yes | InboundPort | Textbox | Integer
|  | InboundBackEndPort |  | Yes | InboundBackEndPort | Textbox | Integer
|  | LoadBalancerRuleName |  | Yes | LoadBalancerRuleName | Textbox
|  | LoadBalancingProtocol |  | Yes | LoadBalancingProtocol | Drop Down | tcp','udp'
|  | LoadBalancingPort |  | Yes | LoadBalancingPort | Textbox | Integer
|  | BackEndPort |  | Yes | BackEndPort | Textbox | integer